## Sheet1
date | description | hours
2025-05-13 | preparing inventory data by changing formats and allowing barcode information to be added | 4
2025-05-14 | continued preparing inventory data, comunicated with staff about the desired features and requirements of the system | 4
2025-05-15 | continued preparing inventory data, comunicated with staff the process of adding barcodes to different items | 4
2025-05-19 | began barcoding process, adding barcodes to inventory and logging it in the database | 8
2025-05-22 | began wireframing, designing the inventory viewing and editing page. | 4
1900-01-22 | started developing the system, producing the front end of the inventory pages. | 4